ZO/FENG/2026/04/08 Appendix No. 4 – minimum scope of the agreement

- Scope of Services

The services have been divided into 3 PARTS, and a separate agreement shall be concluded for each Part:

PART I - Non-GLP study of perfusion of isolated porcine kidneys with subsequent reperfusion

PART II - Non-GLP study of porcine kidney perfusion in an autotransplantation model

PART III - CONDITIONAL - Study of porcine kidney perfusion in an autotransplantation model under GLP standards

Part III of the Order is conditional in nature and shall be carried out only if the specified conditions are met, i.e., if positive results are obtained from Part I and Part II, understood as the Client's confirmation, on the basis of the results, reports, data, protocols, or other documentation obtained under Part I and Part II, that further implementation of Part III is justified from the perspective of the purpose of the Order and the Project.

With respect to Part III, a conditional agreement shall be concluded, the entry into force and performance of which are contingent upon satisfaction of the condition indicated above.

The Client shall inform the Contractor whether the condition has or has not been satisfied no later than 30 days before the start of Stage I of Part III.

If the condition referred to above is not satisfied, Part III shall not be carried out, and the Contractor shall have no claims whatsoever against the Client on that account.

Until satisfaction of the condition is confirmed, the Client shall not be obliged to pay any remuneration in respect of Part III of the order.

The Contractor acknowledges that the conditional nature of Part III results from the phased nature of the Order, the purpose of the Project, and the need to assess the results obtained under Part I and Part II before a decision is made to carry out the study under GLP standards.

Standard of Performance of the Service

With respect to Part I and Part II, the Contractor shall perform the studies in the non-GLP standard, with due diligence, in accordance with current scientific knowledge, the agreed study protocol, the Contractor's internal procedures, and applicable provisions of law.

With respect to Part III, the Contractor shall perform the study in the GLP standard, in accordance with the applicable requirements of Good Laboratory Practice, the agreed study protocol, the Contractor's quality procedures, and applicable provisions of law.

- Division of Parts into Stages and Payment Terms

Each of the above PARTS shall be divided into 3 stages:

Stage I: preparation of the study protocol, preparatory work;

Stage II: performance of perfusion and subsequent reperfusion/autotransplantation (depending on the Part);

Stage III: Biochemical analyses.

Completion of each Stage requires the Client's confirmation of proper performance in a handover and acceptance protocol. The basis for acceptance of a Stage shall be performance of the work provided for that Stage and delivery to the Client of the results, documents, data, reports, protocols, or other materials required for that Stage in accordance with the Agreement, the study protocol, the schedule, or the request for proposals.

If defects, deficiencies, non-compliance with the study protocol, the Agreement, GLP principles—if applicable—or other requirements specified in the procurement documentation are identified, the Client may refuse to sign the handover and acceptance protocol until the irregularities are remedied, or may sign the protocol subject to reservations. In such case, the payment period shall run from the date on which the Client is served with a correctly issued VAT invoice and the handover and acceptance protocol signed without reservations, or from the date on which the Client confirms that the reservations have been remedied.

Payment amounts for each performance stage:

Stage I – advance payment up to 100%; provided that the detailed amount of the advance payment, the conditions for its disbursement, and any obligation to refund it in the event of non-performance or improper performance of Stage I shall be specified in the Agreement;

Stage II – advance payment: maximum 40%;

partial payment: maximum 30%, payable after completion of 50% of the experiments commissioned under the stage;

the remaining amount payable after completion of the stage;

Stage III – 100% upon completion of the stage.

The Client undertakes to settle the amount due by bank transfer within 7 to 30 days (the exact period to be agreed at the contract-signing stage) from the date of delivery to the Ordering Party’s registered office of a correctly issued VAT invoice and a handover and acceptance protocol confirmed by the recipient.

- Materials Supplied by the Client

The list of materials supplied by the Client is included in the detailed request for quotation.

The delivery date of the materials by the Client shall be determined after the agreement with the Contractor is signed.

Consequences of delay in the delivery of materials by the Client:

- The Client shall pay a contractual penalty for delay in the amount of up to 0.2% of the net value of the relevant Stage for each day of delay

- Materials Provided by the Contractor

The Contractor shall provide everything necessary to perform the service, except for the materials provided by the Client.

- Service Completion Date

The service completion date has been specified by the Client in the request for quotation.

- Contractual Penalties

Consequences of delay in performance of the service by the Contractor in the amount of up to 0.2% of the net value of the relevant Stage for each day of delay.

- IP Rights

  - For the purposes of the Agreement, “Results” shall mean all results, effects, data, information, documents, materials, and studies created, obtained, produced, collected, or recorded by the Contractor, subcontractors, or other persons acting for the Contractor in connection with performance of the Order, regardless of form, manner of fixation, or degree of completion, including in particular: raw data, source data, interim results, final results, reports, protocols, analyses, compilations, study documentation, quality documentation, GLP/non-GLP documentation, laboratory records, photographic documentation, documentation concerning samples and biological material, know-how, technical, technological, scientific, and research information, works, databases, inventions, technical solutions, discoveries, improvements, modifications, and other results capable of being used by the Client.

  - All Results obtained by the Contractor in the course of performing the Order shall belong to the Client.

  - The parties to the procedure agree that the right to obtain patents, rights of protection for utility models, and rights arising from the registration of industrial designs, the subject matter of which constitutes the Results, shall belong to the Client. The Contractor shall not be entitled to any additional remuneration on this account.

  - The Client shall be entitled to make filings and pay fees aimed at securing legal protection for the Results before the competent authority. The Client shall bear all costs related to the above protection.

  - At the same time, the Contractor undertakes to cooperate with the Client in connection with filings of industrial property rights with the competent authority, including by providing the Client with documents and information necessary to prepare the descriptions contained in the filing.

  - As part of the remuneration for performing the Order, to the extent that the Results constitute works within the meaning of Copyright Law, upon creation of the Results, the Contractor hereby transfers to the Client all economic copyrights in the Results, and the Client acquires them in all existing fields of exploitation (“Fields of Exploitation”), in particular:

- recording the Results, without any quantitative limitations, by any technique, including printing, digital, reprographic, electronic, photographic, optical, laser, magnetic recording, on any medium, including electronic, optical, magnetic media, floppy disks, CD-ROMs, DVDs, and paper;

- reproducing the Results, without any quantitative limitations, by any available technique, including printing, reprographic, digital, electronic, laser, photographic, magnetic or optical recording, on any medium, including electronic, optical, magnetic media, floppy disks, CD-ROMs, DVDs, and paper, within an online system;

- with respect to circulation of the original or copies on which the Results have been fixed—placing them on the market, rental, lease, lending, granting licenses or sublicenses;

- use of the Results for the purposes of patent filings for inventions;

- use of the Results for the purposes of preparing tender documentation and contract documentation in order to commercialize the Results;

- broadcasting by wired or wireless vision or sound transmission by terrestrial stations, via satellite (coded and uncoded signal), together with the right to retransmit within digital platforms or cable networks;

- entering the Results into computer memory and multimedia networks, including the Internet and internal Intranet-type networks, without any quantitative limitations, as well as transmitting the Results within the above networks, including simultaneous integral online retransmission (rebroadcasting) by another radio or television organization;

- public performance, exhibition, display, or playback, in any form, in particular at all shows, fairs, exhibitions, and open and closed events, ticketed and non-ticketed—regardless of the type and size of the audience;

- with respect to dissemination of the Results and copies thereof in a manner other than that specified above—making works publicly available in such a way that anyone may access them at a place and time of their choosing; on the Internet;

- use of the Results in whole or in part, including as part of compilations or combinations with other works, artistic performances, phonograms, or videograms, supplemented with commercial, promotional, or advertising content, including for advertising and promotional purposes (without limitations as to the form and manner of advertising);

- exploitation in whole or in part by means of any new technologies;

- use of the Results in whole or in any part as a company sign used to designate the enterprise, including placing it in particular on company letterhead, forms, labels, advertising materials, brochures, posters, and information materials.

  - At the same moment, as part of the remuneration, to the extent that the Results constitute databases not protected under Copyright Law, the Contractor transfers to the Client the right to extract data from the databases and the right to re-use them.

  - At the same time, the Contractor transfers to the Client, and the Client acquires, the right to exercise and authorize the exercise of derivative rights in adaptations of the Results in the Fields of Exploitation.

  - The Contractor also authorizes the Client to exercise and authorize the exercise of derivative rights in adaptations of the Results in the Fields of Exploitation by third parties, together with the right to grant further such authorizations by subsequently authorized entities, and undertakes not to revoke this authorization under penalty of liability for damages.

  - The Contractor hereby additionally authorizes the Client to create adaptations of databases constituting the Results, protected under Copyright Law, and undertakes not to revoke this authorization under penalty of liability for damages.

  - The Contractor authorizes, and undertakes not to revoke under penalty of liability for damages:

- the exercise of the moral rights in the Results by the Client,

- authorization by the Client for third parties to exercise the moral rights in the Results, together with the right to grant further such authorizations by subsequently authorized entities.

  - The Contractor represents and warrants that it has acquired or will acquire from the creators of the Results, within the meaning of Copyright Law, the full scope of rights in the Results, including the right to obtain industrial property rights, all economic copyrights, the right to authorize the creation of adaptations and the exercise of derivative rights, as well as any other authorizations necessary to grant the Client the rights and authorizations specified in the Agreement. At the same time, the Contractor undertakes that neither it nor the creators of the Results, within the meaning of Copyright Law, will exercise the moral rights in the Results with respect to the inviolability of the content and form of the Results, their reliable use, supervision over the manner of use of the Results, and the decision on the first disclosure of the Results to the public, vis-à-vis the Client, its legal successors, licensees, and the current owner of the economic copyrights in the Results.

  - The Contractor undertakes that, should new Fields of Exploitation arise, it shall transfer to the Client the economic copyrights to dispose of and use the Results in such new Fields of Exploitation within the remuneration specified in the Agreement—the Contractor shall not be entitled to any additional remuneration on this account.

  - At the Client's request, the Contractor undertakes to provide all documents confirming that the creators of the Results, within the meaning of Copyright Law, have granted the consents and assumed the obligations provided for in this Agreement.

  - If the Results are published, the Parties shall agree on the co-authors of the publication.

  - The Parties undertake to inform each other without delay of any third-party claims asserted with respect to the Results.

  - The Contractor undertakes to deliver to the Client the Results, including interim Results, raw data, study documentation, GLP/non-GLP documentation, reports, protocols, analyses, and other materials created in connection with performance of the Order, within the time limits and in the form specified in the Agreement, the study protocol, the schedule, or at the Client's request, to the extent necessary to verify proper performance of the Order, accept the work, conduct an audit, protect IP, settle the Project, or make further use of the Results by the Client.

  - The Contractor shall not be entitled to use the Results, including interim Results, raw data, reports, protocols, study documentation, GLP/non-GLP documentation, or the Client's know-how, for purposes other than proper performance of the Agreement, without the Client's prior written consent.

  - The Contractor undertakes to inform the Client without delay of the creation of any Results that may be subject to legal protection, in particular as an invention, utility model, industrial design, work, database, know-how, or trade secret, and to refrain from any actions that could prevent or hinder the Client's obtaining, maintaining, or exercising rights to such Results.

- Terms for Amendment of the Agreement

8.1. The provisions of the Agreement may be amended upon the consent of both Parties, in the form of a written amendment, otherwise null and void, in the following cases:

- a change in the deadline for performance of the Agreement, including the schedule for performance of the Parts or Stages, if the change is necessary due to reasons preventing performance of the Order within the assumed deadline;

- a change in payment dates and terms if they result from changes introduced by the Parties to the Agreement, the need to change the method of settlement under the Agreement or the making of payments to the Contractor due to previously unforeseen circumstances, or changes to the Project co-financing agreement, guidelines concerning performance of the Order, or the rules on eligibility of expenditures;

- changes concerning the name and registered office of the Client or the Contractor, their organizational and legal form, bank account numbers, or other identification data during the term of the Agreement, or legal succession;

- a change intended to correct obvious clerical, accounting, or editorial errors in the Agreement;

- a change in the persons through whom the Contractor performs the subject matter of the Agreement, replacing them with other persons having at least equivalent qualifications, experience, and authorizations,

- a change of subcontractor or in the scope of work entrusted to a subcontractor, provided that the Client is informed in advance and it is demonstrated that the subcontractor has the qualifications, experience, technical, organizational, and personnel resources necessary for proper performance of the entrusted work,

- a change in the manner of performance of the Agreement, if such change is necessary for technical, scientific, organizational, regulatory, ethical, safety, or quality reasons, provided that the change does not alter the general nature of the Agreement or the subject matter of the Order;

- a change resulting from amendments to generally applicable provisions of law, decisions, recommendations, or guidelines of competent authorities, requirements of ethics committees, GLP principles, if applicable, or other regulatory requirements affecting performance of the Agreement.

8.2. Amendments to the Agreement referred to in Section 8.1 shall be permissible only to the extent consistent with the procurement documentation, the competitiveness principle, the Guidelines on the Eligibility of Expenditure for 2021–2027, the Project co-financing agreement, and generally applicable provisions of law.

8.3. An amendment to the Agreement may not lead to circumvention of the outcome of the procurement procedure, breach of the principle of equal treatment of contractors, fair competition, or transparency of the procedure, nor may it alter the general nature of the Agreement or the subject matter of the Order.

- Termination of the Agreement / Withdrawal from the Agreement

9.1. The Client shall have the right to withdraw from the Agreement in whole or in part within 30 days from the date on which it learned of the circumstance justifying withdrawal, in the event of:

a) a material change in circumstances, independent of the Client, which could not have been foreseen at the time of conclusion of the Agreement, causing performance of the Agreement not to be in the public interest or to remain contrary to the purpose for which the order was awarded,

b) a delay by the Contractor indicating that timely performance of the Agreement is unlikely,

c) a material breach of the provisions of the Agreement by the Contractor,

d) issuance of an order to seize the Contractor's assets or application of an enforcement or security measure jeopardizing proper performance of the Agreement.

9.2. Before exercising the right of withdrawal, the Client may set the Contractor an appropriate additional period for proper performance of the Agreement or remedying the breaches, unless the circumstances indicate that this would be pointless.

9.3. The Client shall have the right to terminate the Agreement in whole or in part with future effect, subject to 14 days' notice, in the event of loss of the funding source for the order in whole or in part, or a permanent shift in funding sources that makes further performance of the Agreement in accordance with its purpose or scope impossible.

9.4. In the event of withdrawal from or termination of the Agreement, the Contractor shall only be entitled to remuneration for the part of the Agreement properly performed up to the date of withdrawal or termination, provided that the result of such work can be used by the Client in accordance with the purpose of the Agreement.

9.5. The value of the work referred to in Section 9.4 shall be determined on the basis of the provisions of the Agreement, the physical and financial schedule, the degree of actual progress of the work confirmed by an inventory protocol, and documents submitted by the Contractor. Work not performed, performed defectively, or useless to the Client shall not be remunerated.

9.6. Reimbursement of costs other than remuneration for the work performed shall be due only where the obligation to reimburse them follows directly from the Agreement, and such costs have been duly documented and shown to be directly related to performance of the Agreement, unavoidable, and impossible to recover.

9.7. Within 7 days from the date of delivery of the notice of withdrawal or termination of the Agreement, the Parties shall prepare an inventory protocol of the work performed, work in progress, and results that may be used by the Client.

9.8. If no agreement is reached as to the scope or value of the work or costs, the Client shall prepare a protocol and determine the value of the amount due for settlement on the basis of the documentation in its possession, taking into account the Contractor's position, without prejudice to the Contractor's right to pursue claims under general rules.

9.9. Withdrawal from or termination of the Agreement shall not exclude the Client's right to pursue contractual penalties, damages, and other claims arising from the Agreement or provisions of law.

9.10. In the event of withdrawal from the Agreement, termination of the Agreement, or its expiry, regardless of the reason, the Contractor shall be obliged, without delay and no later than within 7 days from the date of service of the notice of withdrawal from the Agreement or termination of the Agreement, to deliver to the Client all results of work performed by that date, including in particular interim results, raw data, reports, protocols, study documentation, quality documentation, GLP/non-GLP documentation, laboratory records, photographic documentation, technical correspondence, and other materials created or collected in connection with performance of the Agreement.

9.11. The Contractor shall also be obliged to return or hand over to the Client, in accordance with the Client's instructions, all materials, samples, products, documents, data carriers, and information provided to the Contractor by the Client in connection with performance of the Agreement, subject to archival obligations arising from mandatory provisions of law or GLP requirements.

912. Withdrawal from the Agreement, termination of the Agreement, or its expiry shall not affect the effectiveness of the provisions regarding confidentiality, intellectual property rights, rights to the Results, the prohibition on using the Client's information, archival obligations, liability for damages, contractual penalties, settlement of performed work, and the obligation to cooperate in the handover of documentation and results.

9.13. Upon creation of individual Results, including interim Results, the Client acquires rights to such Results on the terms specified in the Agreement, regardless of any subsequent withdrawal from the Agreement, termination of the Agreement, or its expiry. To the extent that additional declarations or execution of documents are required for the effective transfer of rights, the Contractor undertakes, without delay and at the Client's request, to make such declarations or sign such documents.

9.14. Where further storage, transport, use, or disposal of biological material, samples, waste, or substances used in performance of the Agreement requires compliance with specific legal, sanitary, environmental, ethical, or quality requirements, the Contractor shall act in accordance with applicable provisions of law, decisions of competent authorities, approvals of ethics committees, GLP procedures, if applicable, and the Client's written instructions.

- The Agreement shall be governed by Polish law

- Subcontracting Part of the Work

11.1. The Contractor's obligations may be transferred to third parties only with the Client's prior written consent, failing which such transfer shall be null and void.

11.2 The Contractor is obliged to present the Client with documents confirming that the subcontractor has the necessary qualifications, experience, authorizations, research equipment, technical and organizational resources, and a team of research staff ensuring proper performance of the Agreement for the Client.

11.3. The Contractor may entrust performance of part of the Order to subcontractors, provided that proper performance of the subject matter of the Order is ensured and full responsibility for the acts and omissions of subcontractors is retained as for its own acts and omissions.

11.4. If the Contractor intends to entrust performance of part of the Order to subcontractors, the Contractor shall inform the Client in advance of the scope of the entrusted activities and of the subcontractors involved in performance of the Order, and shall also obtain the Client's consent referred to in Section 11.1.

11.5. The Contractor shall bear full responsibility for proper performance of the Agreement, including for the acts and omissions of subcontractors, third parties, employees, associates, advisers, and other persons or entities used in performance of the Agreement, as for its own acts and omissions. Such responsibility shall include, in particular, research errors, surgical errors, organizational errors, breaches of the study protocol, GLP principles—if applicable—provisions of law, ethical standards, requirements of ethics committees, confidentiality obligations, rules for handling biological material, samples, substances, and waste, as well as obligations concerning delivery of Results and documentation.

11.6. Agreements concluded between the Contractor and subcontractors should, in particular:

a) clearly specify the scope of responsibility of the parties;
 b) ensure the Client access to information, documentation, and Results of work created in connection with performance of the Order to the extent necessary to verify its proper performance;
 c) ensure the Client's ability to conduct an audit at the subcontractor's premises to the extent related to performance of the Order;
 d) oblige the subcontractor to maintain confidentiality at least to the extent corresponding to the Contractor's obligations under the Agreement;
 e) ensure the effective transfer to the Client of rights to Results created with the subcontractor's involvement, or the Client's obtaining rights to use such Results to the extent specified in the Agreement;
 f) oblige the subcontractor to comply with applicable provisions of law, requirements of ethics committees, the study protocol, quality requirements, GLP principles—if applicable—and rules for handling biological material, samples, substances, and waste.

11.7. The Contractor is obliged to ensure that confidentiality agreements (NDAs) are concluded with subcontractors, covering all information obtained in connection with performance of the Order, including the Client's technical, technological, organizational, research information and know-how.

11.8. Entrusting performance of part of the Order to a subcontractor shall not release the Contractor from any obligations or liability arising from the Agreement, the procurement documentation, the study protocol, provisions of law, requirements of ethics committees, GLP principles—if applicable—or any other requirements concerning performance of the Order.

11.9. Any change of subcontractor or in the scope of work entrusted to a subcontractor requires prior notice to the Client and the Client's consent, as well as demonstration that the new subcontractor has the qualifications, experience, technical, organizational, and personnel resources necessary for proper performance of the entrusted work.

- Audit

12.1. During the study, the Client may conduct an audit of the Contractor and subcontractors in order to verify the conditions under which the study is conducted, compliance of performance of the Agreement with its provisions, the procurement documentation, the study protocol, quality requirements, GLP principles—if applicable—and applicable provisions of law.

12.2. Identification during the audit of material irregularities that may affect proper performance of the Agreement, reliability of the Results, safety, compliance with GLP, if applicable, or compliance with applicable provisions of law shall entitle the Client to suspend acceptance of the relevant Stage, refuse acceptance of work performed not in accordance with the Agreement, demand that the irregularities be remedied, charge contractual penalties, or exercise other rights provided for in the Agreement or by law.

- Waste management

13.1. The subject matter of the analyses will include, among others, products containing perfluorinated compounds; therefore, the Contractor must ensure that the procedures used comply with currently applicable laws governing the use of perfluorinated compounds and the handling of waste containing perfluorinated compounds, including in particular laws concerning hazardous substances, waste management, hazardous waste, environmental protection, and occupational health and safety.

13.2. The Contractor undertakes to ensure the lawful storage, labeling, transport, recordkeeping, transfer for further management, recovery, or disposal of all waste generated in connection with performance of the Agreement, including waste containing perfluorinated compounds, biological material, samples, product residues, reagents, and other substances or materials requiring special handling.

13.3. The Contractor undertakes to perform the obligations referred to above using entities holding the licenses, registrations, authorizations, or administrative decisions required by law, if such are required for the given type of activity or waste.

13.4. At the Client's request, the Contractor shall provide documents, procedures, statements, records, waste transfer cards, confirmations of disposal, or other documents confirming that the handling of waste and substances used in performance of the Agreement complies with applicable provisions of law.

13.5. The Contractor shall bear full responsibility for proper handling of waste, hazardous substances, biological material, samples, and residues generated in connection with performance of the Agreement, including for the acts and omissions of subcontractors and other entities used in performance of the Agreement.